## Slide 1: Quantum Materials Laboratory: 5-Year Recruitment and Team Development Plan
Year 1 (Laboratory Setup Phase)
  Recruitment: 2 Ph.D. students, 2 postdoctoral researchers, and 1–2 undergraduate students (to participate in lab setup)
  Division of Roles: Postdocs will take the lead in building the platform and producing initial results; Ph.D. and undergraduate students will integrate into the platform
  Goal: Quickly establish the instrumentation platform and produce the first high-quality data/preprints
Years 2–5 (Rolling Expansion)
  Add 1–2 new Ph.D. students each year (depending on projects/funding)
  Team Size Limit: ≤ 6 Ph.D. students (excluding those jointly supervised with other faculty)
  Maintain 1–2 postdocs; have 2–4 rotating undergraduates involved in short-term planned projects
  Senior Ph.D. students may mentor 1 undergraduate: for short-term projects/Ph.D. preparatory training
Recruitment Preferences and Philosophy
  Prioritize recruiting Ph.D. students: they are more adaptable and beneficial for medium- to long-term projects and team renewal
  Include postdocs in the early stage: accelerate platform construction and rapidly produce representative results (drawing on wording leading group's experience)
  Joint Training: Ph.D. students co-supervised with other on-campus faculty will not count towards our Ph.D. student limit
Stage Milestones (Illustrative)
  Y1: Platform construction completed, first batch of data/preprints
  Y2–Y3: Stable publications, expand research lines and instrument capabilities
  Y4–Y5: Build a talent pipeline and achieve landmark results, consolidating international influence
Note: Scale and pace will be dynamically adjusted based on project progress, funding and talent supply